## Blackbox Testing
User Acceptance Testing
Test Scenario ID | Test Scenario Description | Business Impact (e.g., High, Medium, Low) | Test Case ID | Test Case Description | Test Type | Test Steps | Preconditions | Test Data | Test Coverage | Post Conditions | Expected Result | Actual Result | Status | Executed By | Executed Date | Comments
SR01 | Provide input values within the expected range and verify that the program produces a reasonable prediction. | Medium | TC01 | Provide input values within the expected range and verify that the program produces a reasonable prediction. | User Acceptance | 1.Open program 2.enter input values 3.start the prediction process | program is installed and running | [0,42,52812.09301,15609.38091,138961.2505] | Statement | Prediction shown on screen | program should displays a predicted value within a range based on the input values | program displays a predicted value within the range | Passed | Harry Bennett | 2023-09-04
SR02 | Test with the minimum and maximum values for each input feature to ensure the model's behavior at the boundaries. | High | TC02 | Test with the minimum values for each input feature to ensure the model's behavior at the boundaries. | User Acceptance | 1. open the program 2. enter the min values 3. start prediction | program is running | Example of min values [0,12,10235,00024.11,200215,10124] | Statement | Prediction shown on screen | the predicted value should be valid with the provided min values | the predicted was valid after Min values were provided | Passed | Harry Bennett | 2023-09-04
SR02 | Test with the minimum and maximum values for each input feature to ensure the model's behavior at the boundaries. | High | TC02 | Test with the maximum values for each input feature to ensure the model's behavior at the boundaries. | User Acceptance | 1. open the program 2. enter the Max values 3. start prediction | program is running | Example of max values [0,42,62812.09301,15609.38091,138961.2505] | Statement | Prediction shown on screen | the predicted value should be valid with the provided min values | the predicted was valid after Max values were provided | Passed | Harry Bennett | 2023-09-04
SR03 | Test with missing values in input features and verify that the program handles them gracefully. | Low | TC03 | Test with missing values in input features and verify that the program handles them gracefully. | User Acceptance | 1.Open Code 2.enter min and max values 3.run program | program is installed and running | [0,42,62812.09301,15609.38091,138961.2505] | Statement | Prediction shown on screen | data should not work as min values are 5 | program does not run | Failed | Harry Bennett | 2023-09-04 | FIX THE CODE
SR03 | Test with missing values in input features and verify that the program handles them gracefully. | Low | TC03 | Test with missing values in input features and verify that the program handles them gracefully. | User Acceptance | 1.Open Code 2.enter min and max values 3.run program | program is installed and running | [0,42,62812.09301,15609.38091,138961.2505] | Statement | Prediction shown on screen | data should not work as min values are 5 | program does not run | Passed | Harry Bennett | 2023-09-04 | FIXED THE CODE: def preprocess_data(data): # Checking for any missing values if data.isnull().any().any(): raise ValueError("The data contains missing values! Please check the data is cleaned before processing.") if __name__ == "__main__": try: #add try except to handle missing value error data = load_data('Car_Purchasing_Data.xlsx') ScaledOX, ScaledOY, sc, sc1 = preprocess_data(data) TrainOX, TestOX, TrainOY, TestOY = split_data(ScaledOX, ScaledOY) models = train_models(TrainOX, TrainOY) rmse_values = evaluate_models(models, TestOX, TestOY) plot_model_performance(rmse_values) save_best_model(models, rmse_values) loaded_model = load("car_model.joblib") predict_new_data(loaded_model, sc, sc1) except ValueError as ValError: print(f"Error: {ValError}")
SR04 | Test the program's ability to switch between different machine learning models. | High | TC04 | Test the program's ability to switch between linear regression machine learning models. | User Acceptance | 1: Open Program 2:Must switch to linear regression 3:verify model switch | program is installed and running | None | Statement | program shows Linear Regression model as active model. | The program shows Linear Regression model is active after selecting the switch | Program does not display "Linear Regression model" name | Failed | Harry Bennett | 2023-09-04 | FIX THE CODE
SR04 | Test the program's ability to switch between different machine learning models. | High | TC04 | Test the program's ability to switch between linear regression machine learning models. | User Acceptance | 1: Open Program 2:Must switch to linear regression 3:verify model switch | program is installed and running | None | Statement | program shows Linear Regression model as active model. | The program shows Linear Regression model is active after selecting the switch | Program displays linear regression model | Passed | Harry Bennett | 2023-09-04 | FIXED THE CODE: def train_models(TrainOX, TrainOY): NameOModels = [ 'Linear Regression', 'Support Vector Machine', 'Random Forest', 'Gradient Boosting Regressor', 'XGBRegressor' ] models = {} for name in NameOModels: #Display model name print(f"Training model: {name}") model = ModelFactory.get_model(name) model.fit(TrainOX, TrainOY.ravel()) models[name] = model #display when model trained successfully print(f"{name} trained successfully.") return models
SR04 | Test the program's ability to switch between different machine learning models. | High | TC04 | Test the program's ability to switch between different Support Vector Machine learning models. | User Acceptance | 1: Open Program 2:Must switch to support vector machine 3:verify model switch | program is installed and running | None | Statement | program shows Support Vector Machine model as active model. | The program shows Support Vector Machine model is active after selecting the switch | Program does not display "Support Vector Machine" name | Failed | Harry Bennett | 2023-09-04 | FIX THE CODE
SR04 | Test the program's ability to switch between different machine learning models. | High | TC04 | Test the program's ability to switch between different Support Vector Machine learning models. | User Acceptance | 1: Open Program 2:Must switch to support vector machine 3:verify model switch | program is installed and running | None | Statement | program shows Support Vector Machine model as active model. | The program shows Support Vector Machine model is active after selecting the switch | Program displays support vector machine is active | Passed | Harry Bennett | 2023-09-04 | FIXED THE CODE: def train_models(TrainOX, TrainOY): NameOModels = [ 'Linear Regression', 'Support Vector Machine', 'Random Forest', 'Gradient Boosting Regressor', 'XGBRegressor' ] models = {} for name in NameOModels: #Display model name print(f"Training model: {name}") model = ModelFactory.get_model(name) model.fit(TrainOX, TrainOY.ravel()) models[name] = model #display when model trained successfully print(f"{name} trained successfully.") return models
SR05 | Confirm that the program successfully trains the selected model with the provided training data. | High | TC05 | Confirm that the program successfully trains the selected model with the provided training data. | User Acceptance | 1:Open program 2:select linear regression 3:start the model training process with the provided data | program is installed and running | Provided Training Data | Statement | Model training is complete. | The program should show a confirmation message when successful model training. | Program does not show the message about successful training of data. | Failed | Harry Bennett | 2023-09-04 | FIX THE CODE
SR05 | Confirm that the program successfully trains the selected model with the provided training data. | High | TC05 | Confirm that the program successfully trains the selected model with the provided training data. | User Acceptance | 1:Open program 2:select linear regression 3:start the model training process with the provided data | program is installed and running | Provided Training Data | Statement | Model training is complete. | The program should show a confirmation message when successful model training. | Program does not show the message about successful training of data. | Passed | Harry Bennett | 2023-09-04 | FIXED THE CODE: def train_models(TrainOX, TrainOY): NameOModels = [ 'Linear Regression', 'Support Vector Machine', 'Random Forest', 'Gradient Boosting Regressor', 'XGBRegressor' ] models = {} for name in NameOModels: #Display model name print(f"Training model: {name}") model = ModelFactory.get_model(name) model.fit(TrainOX, TrainOY.ravel()) models[name] = model #display when model trained successfully print(f"{name} trained successfully.") return models
SR06 | Provide a set of inputs for which you know the expected output. Verify that the program's prediction matches the expected value. | Low | TC06 | Provide a set of inputs for which you know the expected output. Verify that the program's prediction matches the expected value. | User Acceptance | z |  |  | Statement |  |  |  | Passed | Harry Bennett | 2023-09-04
SR07 | Test the model's performance with different input combinations and compare the predicted values against actual values. | Medium | TC07 | Test the model's performance with different input combinations and compare the predicted values against actual values. | User Acceptance |  |  |  | Statement |  |  |  | Passed | Harry Bennett | 2023-09-04
SR08 | Check if the program's visualization (the performance comparison bar chart) accurately represents the model's RMSE values. | Medium | TC08 | Check if the program's visualization (the performance comparison bar chart) accurately represents the model's RMSE values. | User Acceptance |  |  |  | Statement |  |  |  | Passed | Harry Bennett | 2023-09-04
SR09 | Test if the program correctly saves and loads the trained model using the joblib library. | Medium | TC09 | Test if the program correctly saves and loads the trained model using the joblib library. | User Acceptance |  |  |  | Statement |  |  |  | Passed | Harry Bennett | 2023-09-04
SR10 | Verify that the loaded model produces the same predictions as the original trained model. | Medium | TC10 | Verify that the loaded model produces the same predictions as the original trained model. | User Acceptance |  |  |  | Statement |  |  |  | Passed | Harry Bennett | 2023-09-04
SR11 | Use the predict_new_data function to test the program's ability to predict new data points. | High | TC11 | Use the predict_new_data function to test the program's ability to predict new data points. | User Acceptance |  |  |  | Statement |  |  |  | Passed | Harry Bennett | 2023-09-04
SR12 | Verify that the predicted output matches your expectations based on your understanding of the data. | High | TC12 | Verify that the predicted output matches your expectations based on your understanding of the data. | User Acceptance |  |  |  | Statement |  |  |  | Passed | Harry Bennett | 2023-09-04